## WBS Template
ANTI RAGGING PORTAL
Sr.No | Module | Use Case | Work Item / Screen / Task | Start Date | End Date | Remark
A
1 | ADMINISTRATOR | Login | To access the potral | 7//2019 | 2012-07-22
|  | Update Status | Start accesssing | 2019-07-26 | 2019-07-26
|  | check for pending request. |  | 2019-07-26 | 2019-07-26
check for feedback.
B
2 | STUDENT | Register, Login, Logout | Register and Login. | 2019-07-22 | 2019-07-23
|  | Raise their complaint | Raise the complaint of the ragging with description | 2019-07-27 | 2019-07-27
|  | Give feedback. | Give the feedback of the complaint being resolved | 2019-07-27 | 2019-07-28
|  | Check Status | Check the status of their complaint